## Bug Report
Defect Report
Project Details
Description |  |  | Voluntary Beta Testing
Tester, contact |  |  | Benedek Sándor Seres, benedek.seres@gmai.com
Testing Date |  |  | 01-Aug-2023 - 09-Aug-2023
Test Environment |  |  | Beta version
BugID | Short Description | Description | Steps for Reproduction | Expected Result | Actual Result | Priority
Locnew 1 | Clipping through tire swing model hanging from tree | the tire swing that is hanging from the tree behind the house the game's first quest takes place is not solid and player can clip through it | Go behind the house the first quest takes place | the tire swing model is solid | the tire swing model is not solid and player can go through it | Low
find the tire swing
go through it
Locnew 2 | Missing collision | There is a minor collision missing between the mountain and the grass at the end of the street where the white school bus is | get to the back of the house behind the white school bus | all terrain has collision | back of the house near the white school bus has missing collision | Medium
go to the trees near where the mountain starts
Locnew 3 | Pause menu overlapped by the Day title | Starting a day and pausing the game during the Day title causes the pause menu to be overlapped | Start a day | the pause menu overlaps everything | the pause menu is overlapped by the day title | Medium
pause the game when the Day title appears
Locnew 4 | Triggered sounds do not stop when game is paused | Triggered sounds do not stop while the game is paused, causing the objects complete their scripted event without sound in the end | find an object with a scripted event and sound | Triggered sounds are paused while the game is paused | Triggered Sounds keep playing while the game is paused | Medium
pause the game
continue playing
wait for the object to finish its routine
Locnew 5 | Mouse is too sensitive | The default sensitivity of the mouse is set too high, making it difficult to do slight look-arounds | Move the mouse vertically with default sensitivity | Default mouse sensitivity allows player to do slight look-arounds | Looking around nicely with default mouse sensitivity is difficult | Medium
Move the mouse horizontally with default sensitivity
Locnew 6 | Music volume of main menu is lower when player enters main menu from the game | Music volume main menu is higher when player starts the game than when player actually plays the game and goes back to the main menu | start the game | Main menu music always has the same volume level | Main menu music is quieter when player enters the main menu from playing | Low
start playing
go back to the main menu
Locnew 7 | Player can go up steep terrain | Player can go up very steep terrain which is unrealistic to the game world's physics. This also allows the player to get near the edge of the world | find a mountain | Player cannot go up very steep terrain | Player can go up very steep terrain and gets to see the edge of the world | Medium
go up the mountain
Locnew 8 | Mouse Y sensitivity is not equally sensitive as Mouse X's on controller | Horizontally the camera is more sensitive than vertically even if they are set to the same level on a controller | set the Mouse Y sensitivity and Mouse X sensitivity to the same level | Horizontal and vertical sensitivity on the same level are equally sensitive | Horizontally the camera sensitivity is more sensitive than vertically even if they are set to the same level | Medium
start playing with a controller
look slightly vertically
look slightly horizontally
Locnew 9 | The explosion on the subscriber number is delayed | When first meeting Cliff Rockslide he mentions the subscribers and how many he aims to have but the effect of explosion happens after he starts changing the subject | meet Cliff Rockslide on Day 1 | The explosion on the number of subscribers happen when he mentions this feature | The explosion on the number of subscribers happen after he talks about money as motivation | Low
talk to him until he mentions the subscribers
see the explosion when he talks about economical gain as motivator
Locnew 10 | Pressing ESC during dialogue option causes player to get stuck | Pressing the ESC button when player gets to say Yes or No during conversation causes the dialogue to stop and player is stuck | get into a conversation | Pressing ESC during dialogue options does not do anything | Pressing ESC during dialogue options causes the dialogue to stop | High
Press ESC when Yes or No options are presented
Locnew 11 | NPC in café does not move | the NPC that is sitting inside the café with a coffee and a book does not move | get to the café | NPCs have natural moving | NPC in café is sitting steady | Low
find the NPC inside the café with a book and coffee
Locnew 12 | Player is pushed up when standing in the way of Cliff Rockslide | When Cliff starts running and player is in the way, Cliff will push the player up | Get ahead of Cliff when he starts running | Cliff Rockslide does not collide with the player | Cliff Rockslide collides with the player causing a glitch | High
Let Cliff get ahead of player
Locnew 13 | Number of subscribers do not reset | The number of subscribers do not reset after gaining at least one on day one and quitting then continuing the game | Retrieve the camera on day 1 | The number of subscribers resets to the number player had before player quitted | The number of subscribers does resets to the number player had before player quitted | Medium
Gain at least one additional subscriber
quit to the main menu
Continue playing by using the Continue function
Retrieve the camera on day 1
check the number of subscribers
Locnew 14 | Lady runs into the mountain after explosion at gas station | After the explosion on day 1, there is a lady that runs aways into the forest and then clipping into the mountain | get to the explosion on day 1 | NPCs do not clip into textures | Lady at the explosion at the gas station runs and clips into the mountain texture | Low
go to the explosion site but do not start the interactions
check a lady running away and follow it
Locnew 15 | The car of the exploded barrel only appears at the moment of explosion | On day 1, the car that has the exploded barrel appears after the explosion and is not in the world prior to it | Finish the dialogue with the officers after reporting the pumpkin | the car that has the barrel that explodes is somewhere around the location it appears in | the car that has the barrel that explodes is nowhere in the world | Low
Locnew 16 | the given stars after reporting can be zoomed at | after completing a report, the player can zoom at the given stars | complete a reporting | the given stars after reporting have a fixed position | the given stars after reporting can be zoomed at | Medium
focus on the given stars
Locnew 17 | Quitting after the car ride is over after wolf chase and continuing causes game to present allow player to play two missions at once | After Cliff is chased by the wolf, gets in the car and gets out at his garage, player can quit. If player hits Continue in the main menu and completes the pumpkin reporting, Cliff will be there to go to the house where the wolf is and he is also there with the officers at the café | Complete the wolf chase sequence and play until Cliff is dropped of at his garage | Quitting and continuing the game resets the completed reports to the beginning of the day | Quitting and continuing the game after wolf chase sequence causes game to offer player to play two missions at the same time | High
quit to the main menu
Continue the game from the main menu
Complete the pumpkin reporting
go to the gas station where Cliff is waiting to go to the house with the wolf in it
go to the café where Cliff is there with the officers
Locnew 18 | Character artwork does not change from Clarence on day 1 | When Cliff and Clarence gets into their dialogue on day 1, the character artwork does not change when Cliff talks | meet Clarence on Day 1 | The character artwork changes based on who is talking | During the dialogue between Cliff and Clarence, only the artwork of Clarence is on screen | Medium
start the conversation between Cliff and Clarence
Locnew 19 | Player can move freely while talking to Oaklyn on day 1 | While talking to Oaklyn on day 1, player can move during the conversation | Start talking with Oaklyn after the explosion on Day 1 | Player cannot move around while in dialogue | Player can move around while in dialogue with Oaklyn | Low
move away
Locnew 20 | The Music volume in the settings changes inconsistently | Turning the Text volume or the SFX volume all the way up, causes the Music volume to go very quiet. This also works if the Music volume is turned down by 1 | Change the music volume by one or change the text volume/SFX volume to max | Changing a volume setting in the options only changes the chosen volume and only one bit at a time | Changing the SFX-Text volume to the max changes the music volume very quiet. This also happens if the Music volume is turned down by 1 | Medium
Locnew 21 | The default SFX volume is the loudest option on the slider | Changing the SFX volume from the default volume causes the volume to go quiet. Even on max volume, the default volume is the loudest | Start the game with the default SFX volume (or change it back to the default and relog to the game) | Changing the default SFX volume causes the SFX volume to go either louder or quieter | Changing the default SFX volume causes the SFX volume to go quieter | Medium
listen to the SFX volume
go back to the main menu
change the SFX volume
start the game
listen to the SFX volume
Locnew 22 | Watching through the opening credits causes the game to start with quieter Music volume | Watching through the opening credits makes the game start with quieter Music volume than when player clicks through it | Launch the game | The music volume does not change unless player changes it | The music volume goes quieter if player watches through the opening credits | Medium
watch through the opening credits
listen to the Music volume
quit from the game to the desktop
launch the game again
skip through the opening credits as soon as the game allows
listen to the Music volume
Locnew 23 | Small dog on day 1 cannot be interacted with | The small dog near the giant pumpkin cannot be interacted with as it cannot be captured for Barking News. It also looks like it's barking it has no sound | Find the small dog on Day 1 | Small dog on day 1 can be interacted with and makes barking sound | Small dog on day 1 has no sound and cannot be interacted with | Low
Locnew 24 | Firefighter is not sitting on box | The firefighter near where the explosion will take place at the gas station of day 1 is not sitting on the box | Find the firefighter near the gas station | NPCs match the height of objects they are sitting on | The firefighter on day 1 is not sitting on the box | Low
Locnew 25 | Police car at the end of day 1 can be clipped through | After the officer takes Cliff home at the end of day 1, her can clipped through | Finish the wolf chase sequence | Objects are solid | Police car at the end of day 1 can be clipped into | Low
after Cliff is taken home, follow the police car
Locnew 26 | Abby clips into her chair on day 2 | When meeting Abby the first time in the game, when she talks, she clips into her chair | Meet Abby on day 2 | NPCs do not clip into textures | Abby clips into her chair on day 2 | Low
Get into a dialogue with her
Locnew 27 | Player is pushed up walking into the giant pumpkins on day 2 | On day 2, walking into the giant pumpkins near the campfire with the four NPCs causes player to be pushed up | Finish the dialogue with Lyla after their father finishes repairing the car | Walking into objects stops player | Walking into the giant pumpkins on day 2 at the back of the farm causes player to be pushed up | Medium
go to the back of the farm
find the giant pumpkins near the campfire
Locnew 28 | SFX volume decreases Text volume | the text volume is normal but goes quieter as soon as an SFX volume is triggered | Get into a dialogue | Text volume is constant | Text volume goes quieter after SFX volume trigger | Low
Listen to the volume of texts
Trigger an SFX volume
Listen to the volume of texts
Locnew 29 | Chilly spawned outside the fences | Chilly the penguin can spawn out of bounds on day 2 | Talk to the Shady Character and successfully start the sequence to look for his penguin | Objects necessary for day completion are inside the player's reach | Chilly once spawned outside the fences where the player cannot get to | Medium
Check if the penguin spawned out of bounds
Locnew 31 | Accessing the giant onion early on day 2 | On day 2 the tractor that is blocking the back of the map can be walked around. This also allows the player to skip the early dialogues | Walk up the fence at the tractor | Objects blocking roads cannot be bypassed | On day 2 the tractor blocking the back of the map can be bypassed | Medium
go along the fence for as long as possible
turn around and go along the fence on the other side for a few meters
Locnew 32 | Getting out of bounds and fall out of the world on day 2 | On day 2, after getting to the back of the farm, player can walk up the mountain. This allows the player to get out of bounds and eventually fall out of the world | get to the back of the farm | Player is blocked from getting out of bounds | Player can get out of bounds on day 2 | Medium
walk forward up to the mountain and at the edge of the world
Locnew 33 | Player running against certain NPCs cause them to move away | Walking into certain NPCs causes them to move away on day 3 | Finish the dialogue with Rose and Lyla | NPCs do not get pushed away if player walks against them | Certain NPCs get pushed away if player walks against them | Low
Walk against Cliff
Walk against Lyla
Walk against Hoss
Walk against Clarence
Walk against Danny
Walk against Hot Doug
Locnew 34 | Player gets stuck at Cliff's pool | Player can be stuck at the pool that Cliff has in his garden if he walks off its edge to the fence near the rubber duck | Go to Cliff's garden | Player cannot get stuck in the game | Player gets stuck at the swimming pool of Cliff | Medium
Go to the swimming pool
walk off its edge to the fence near the rubber duck
Locnew 35 | Firetruck clipped into bench on day 3 | The firetruck on day 3 is clipped into the bench where the kids are playing at the tree | Find the firetruck | Objects are not clipped into one another | The firetruck on day 3 is clipped into the bench | Low
Check the bench
Locnew 37 | Walking into a part of the wall on day 4 upstairs shows skybox | Going up the stairs in the mansion on day 4 near the paintings, walking into a specific part of the wall reveals skybox | Walk up the stairs in the mansion | walking into the wall stops player | walking into a part of wall on day 4 upstairs reveals skybox | Low
go left to the battery arrays
walk into a specific part of the wall between two sets of battery arrays
Locnew 38 | Missing texture in tank battle simulator room | two cupboards are missing textures on one of their sides on day 4 in the mansion | get to the tank battle simulator room | everything has texture | two cupboards are missing textures on day 4 in the tank battle simulator room | Low
check the other side of the "No bullies allowed" cupboard
check the left side of the of cupboard with the sun
Locnew 39 | The interaction range of certain items on day 4 is too high | The interaction range of the second-,third fuses and the key to the 3rd fuse is too high and player can pick them up from anywhere on the level | Reach the interaction range of the 2nd fuse | Interaction range is a constant value | The interaction range of certain items on day 4 is too high | Medium
Go away
pick up the fuse from afar
Reach the interaction range of the key to the 3rd fuse
Pick up the key from afar
Reach the interaction range of the 3rd fuse
pick up the fuse from afar
Locnew 40 | Switches reset by interacting with them again before their animations are completed | The switches at the beginning of day 4 can be reset by interacting with them before their animations are finished | Interact with a switch at the beginning of the mansion | Player cannot interact with the same object before its animation is finished | Player can interrupt the animation of the switches on day 4 by interacting with it again | Low
Interact with the same switch again before the animation is finished
Locnew 41 | Cat statue disappears in Clarence's office | In Clarence's office room, the cat statue disappears in certain angles and distances | Get to Clarence's office room | Objects do not disappear | The cat statue in Clarence's office disappears if player gets into certain angles and distances | Low
Find the cat statue
Walk around the room while looking at the statue
Locnew 42 | Retriggering animations and sound effects with the EDAM | After a fuse is plugged into the EDAM, the player can still interact with the EDAM and trigger the fuse plug in animation. After the EDAM is powered up, player can also retrigger the power up sound | acquire a fuse | the animations and sound effects are triggered when player has something new to interact with the EDAM for | the animations and sound effects can be triggered after their intended use | Low
plug the fuse in the EDAM
interact with the EDAM again
acquire all fuses to charge up the EDAM
interact with the EDAM again
Locnew 43 | Walking up the carrots to the back of the room blocks the player | After walking up on the carrots in the room where the key is for the safe, the player can walk on the boxes and can get trapped if player walks off the edge of the box with the three pumpkins inside | get to the room where the key is kept to the safe | Player cannot get stuck in the game | Player can get stuck in the game by walking off the box with the pumpkins inside | High
walk up the carrots
walk to the box with the pumpkins inside
go off the edge of the box
Locnew 44 | Game has no icon | The game's icon is the Unity icon | Start the game | The game has the same icon when installed as it has on Steam | The game has the Unity icon for the icon | Low
Check the game icon in the taskbar
Locnew 45 | The final fuse can be seen and picked up without pulling out the drawer | Player can acquire the final fuse in the office room if when they enter the room and Bob starts the dialogue, they rush to the drawer where the fuse is without playing through the dialogue | trigger Bob's dialogue when entering the office room | the final fuse cannot be picked up without pulling out the drawer | the final fuse can be picked up if player rushes to the drawer where the final fuse is without playing through Bob's dialogue triggered by entering the room | Medium
rush to the drawer where the final fuse is
Locnew 46 | Pause Menu is inaccessible during the zombie escape sequence | Player cannot bring up the Pause Menu during the zombie escape sequence with the night vision on | reach the point when the zombies escape | the Pause Menu is always accessible | the Pause Menu is inaccessible during the zombie escape sequence | High
press the Menu button
Locnew 47 | Zombies' volume level is inconsistent | The zombies' volume level is only correct when they actually kill the player, otherwise it increases and decreases randomly | reach the point when the zombies escape | The zombies' voices increases or decreases depending on how far they are from player | The zombies' voices increase and decrease randomly with the exception of when they kill the player | Low
run to the ground floor where the zombies cannot be heard yet
let the zombies kill player
run back to the same spot before the zombies after respawning
Locnew 48 | Sometimes a zombie's location is not reset when the player dies | When player is killed, it tends to happen that one of the zombies is not in the cage. This causes the zombies to have an advantage over the player because they can start chasing the player from two different points from the map | reach the point when the zombies escape | the zombies location resets when player dies | Sometimes one of the zombies location does not reset | Medium
let the zombies kill player
check the cage
Locnew 49 | Getting out of bounds and fall out of the world on day 5 | Player can walk up the mountains at the beginning of day 6 and can fall out of the world | Start day 5 | Mountains cannot be walked up on | Mountains can be walked up on day 5 | Medium
walk up the mountains surrounding the starting zone
Locnew 50 | Falling out of the world on day 5 from the lake | Walking around the fence of the lake and walking into and to the mountain results player to fall out of the world | Walk up the mountain besides the fence of the lake | The lake on day 5 cannot be accessed | The fences of the lake on day 5 can be bypassed and can fall out of the world | High
walk into the lake
walk towards to mountains
Locnew 51 | First section of day 5 can be bypassed | By walking up the mountain and dropping down at the cave entrance, player can bypass the first section | walk up the mountains on day 5 | Player needs to play through the first section of day 5 | Player can bypass the first section of day 5 and get to the cave early | High
walk near the entrance to the cave
drop down at the entrance
walk into the cave
Locnew 52 | The zombie chase sequence on day 5 can be accessed early | When getting into the cave and going back out, the zombie chase sequence is triggered | Get into the cave on day 5 | the zombie chase sequence outside the cave starts after they chased player out the cave | The zombie chase sequence can be triggered by walking out the cave | Medium
walk out of the cave
Locnew 53 | The zombie transformation can be triggered without dialogues | If player bypasses the green arrow to trigger the reporting sequence and stands near the cube, the zombie transformation starts | walk to the end of the cave | the zombie transformation is triggered after the dialogue ends at the end of the cave | the zombie transformation can be started if player bypasses the green arrow and walks up to the cube | Medium
walk around the green arrow
walk up to the cube
Locnew 54 | The reporting soundtrack loops if triggered after zombie transformation | If player executes bug Locnew 53 and triggers the reporting sequence, once it is completed the soundtrack of the reporting sequence loops endlessly | execute bug Locnew 53 | the reporting sequence soundtrack stops when the sequence is completed | the soundtrack of the reporting sequence on day 5 can loop endlessly if Locnew 53 is executed prior to triggering it | Low
trigger the reporting sequence by walking into the green arrow
complete the sequence
Locnew 55 | The cube has no collision | If player tries to walk into the cube, they can see the other side of it | try to walk into the cube | the cube has collision and player cannot see through it | the cube has no collision and player can through it if they try to walk into it | Low
see the other side of the cube
Locnew 56 | Clarence can glitch into the prison on day 6 | Clarence glitches into the prison if player plays through the dialogues too fast | Start day 6 | NPCs do not glitch through walls | Clarence glitches through the prison bars into the prison if player plays through the dialogues fast | Low
When Clarence appears at the beginning of the day, play through the dialogues fast
Locnew 57 | the zombies on day 6 push the player up | On day 6 the zombies push the player up causing it to respawn in the air where player is stuck if player is not pushed up against solid texture the player cannot stand on | let the zombies kill player in an open area | Zombies do not push player up | The zombies on day 6 push the player up where the player can get stuck after respawning | High
respawn
let the zombies kill player under the pine trees next to the police station
respawn
let the zombies kill player under solid texture player cannot walk on
respawn
Locnew 58 | getting into textures and leaving causes unstable movement | If player is killed by the zombies in an area where player is pushed up through texture that player cannot stand on, the movement of the player becomes unstable | let the zombies kill player under a unsolid texture | getting into unsolid texture causes player to be popped out and continue playing as normal | getting into unsolid texture causes player to be popped out and continue playing with unstable controls | Medium
respawn
Locnew 59 | dying in Cliff's mom's house can cause player to spin around and get out of bounds | If player lets the zombies kill it in Cliff's mom's house, the player might start spinning around vertically and eventually getting out of bounds | Let the zombies kill player in Cliff's mom's house | If player dies in a building and respawns, the game continues as normal | If player dies in Cliff's mom's house, the player might start spinning vertically and gets out of bounds | High
Locnew 60 | triggering another dialogue without skipping the one triggered by getting the book causes player to freeze | if player does not finish the dialogue triggered by getting the book and player triggers another dialogue, the player freezes | get the book and do not finish the triggered dialogue | triggering a new dialogue while the one triggered by getting the book is active changes the new dialogue to be active and player can continue playing | triggering a new dialogue while the one triggered by getting the book is active causes player to freeze | High
trigger another dialogue
Locnew 61 | The quest items on day 6 can be acquired without triggering the corresponding dialogues | The book and the detonator can be acquired before triggering the corresponding dialogues that prompt player to get them | get the book after escaping from jail | the quest items cannot be acquired without triggering the corresponding dialogues | the quest items can be acquired without triggering the corresponding dialogues | Medium
get the detonator
start the dialogues at Bob's place
Locnew 62 | Player can move before completing the dialogues in the jail | Player can move after Bob starts going back to his shop without completing the dialogue in the jail | start moving once Bob starts going back to his shop | Player cannot move around while in dialogue | player can move when Bob starts going back to his shop | Low
Locnew 63 | Quitting when reaching the energy ring and continuing causes the game to continue incorrectly | When player reaches the energy ring and quits to the main menu and chooses the Continue option, the game mixes different dialogues and jumps to the energy ring where player is stuck | reach the energy ring | Quitting and continuing the game sets player to continue from the last checkpoint | Quitting and continuing the game when reaching the energy ring causes the game to mix dialogues and the player unable to progress | High
quit to the main menu
Continue the game from the main menu
Complete the dialogues
Locnew 64 | When player shoots the cube, the other green arrow remains active | After player successfully shoots the cube, the other green arrow is still available. After walking into it and wait some time, the other one becomes available | Shoot the cube | The green arrows triggering the cube shooting sequence disappear after the sequence is completed | The green arrows triggering the cube shooting sequence do not disappear and can be walked into | Medium
walk into the green arrow
wait until the other green arrow appears
walk into the green arrow
wait until the other green arrow appears
Locnew 65 | Triggering Locnew 64 and letting a cube get the player, the player starts spinning | If player walks into a green arrow after shooting the cube, triggering Locnew 64, the cube can get the player and the player starts spinning | Trigger Locnew 64 | Player does not start spinning by enemy attack | If player triggers Locnew 64 and lets a small cube get player, the player starts spinning | Medium
Let a small cube get player
Locnew 66 | Sgt. Ricks's character artwork changes on day6 | Sgt. Ricks's character artwork changes to her police one during the dialogue after the cube is shot. To achieve this, player needs to be caught by the small cubes by a high number of times that I could not determine | Shoot the cube | The character artwork does not change during a day | Sgt. Ricks's character artwork changes if player is caught a high number of times by the small cubes | Low
let the small cubes get the player a high number of times
finish the dialogues triggered by shooting the cube
Locnew 67 | The trigger point to spawn the small cubes does not work | The trigger point in line of the back of the Cliffmobile does not trigger small cubes if player is caught by them and goes to escape the caves, even though the respawn point of player is behind the trigger point | Shoot the cube | The trigger point spawns small cubes | If player gets rid of the small cubes and goes to escape the caves, the trigger point does not spawn new small cubes | Medium
let the small cubes get the player
respawn
let the small cubes get the player
respawn
go to escape the caves
Locnew 68 | Player cannot leave the Pause menu while dialogue is active during the small cubes chase sequence | If player brings up the Pause menu while the dialogue is active after the small cubes start chasing the team, player cannot leave the Pause menu, only the dialogues continue | Shoot the cube | If the Pause menu is accessible, player can leave from it | Player cannot leave the pause menu if the dialogue after shooting the cube is active | High
wait for the triggered dialogue
Bring up the Pause menu
Locnew 69 | The detonator does not need to be hit to complete day 6 | Player can miss hitting the detonator while escaping from the caves but the game proceeds to day 7 regardless | Shoot the cube | Day 6 does not end if player does not hit the detonator | Day 6 ends if player does not hit the detonator | Low
Run to the entrance of the cave without hitting the detonator
Locnew 70 | Giant pumpkin on day 7 has no collision | The giant pumpkin on day 7 has no collision and player can go inside it | Find the giant pumpkin on day 7 | Objects have collision | The giant pumpkin on day 7 has no collision | Low
Walk into it
Locnew 71 | Characters can be pushed around at the mansion | At Clarence's mansion, before entering the green arrow, all characters, except for Clarence can be pushed around. | walk up to Clarence's team | Characters cannot be moved around by walking into them | On day 7 second phase, all characters can be moved, except for Clarence | Low
walk into everyone except for Clarence
walk into the green arrow
Locnew 72 | Sgt. Ricks's character artwork changes on day 7 | Sgt. Ricks's character artwork changes to her police one during the dialogue after defeating Clarence and his goose as a team | Defeat Trollence and his goose as a team | Character artworks do not change during a day | Sgt. Ricks's character artwork changes after defeating Trollence and his goose as a team | Low
Complete the dialogues after the victory
Locnew 73 | The Live label is missing | The Live label goes missing from getting defeated by Trollence and up until he chases the team with the goose | get defeated by Trollence | The Live label is on screen while receiving stream comments | The Live label is not on screen from the point Trollence defeats the player and up until the goose chase part | Low
get to the part where he chases the player on the goose
Locnew 74 | Trollence can be pushed around | Trollence can be pushed around after the team runs away to the car. This also causes player to start loosing subscribers even before the fight. Once player loses all subscribers, player loses and Trollence is knocked out as if the fight sequence was completed. If player goes to the car, the actual fight starts but Trollence cannot move | Get to the part when Clarence transforms into Trollence | Characters cannot be moved around and the do no harm to the player by walking into them | Trollence can be moved around causing the player to loose subscribers by walking into him and get Trollence stuck | High
Complete the dialogues and wait until the team runs to the car
Walk into Trollence
Reach minus subscribers
go to the car
Locnew 75 | Standing behind the Cliffmobile on day 6 sometimes causes player to spin vertically | In the mines of day 6, if player walks up to the back of the Cliffmobile as close as possible after placing the dynamites, player may start spinning vertically | Place the dynamites | Player does not start spinning by standing in line of moving object | Player may start spinning vertically if stands to the back of the Cliffmobile as close as possible on day 6 after placing the dynamites | Medium
Walk up as close to the back of the Cliffmobile as possible
Locnew 76 | Player can scale the rocks after hitting the detonator resulting in getting stuck on day 6 | In the mines of day 6, player can scale the rocks after hitting the detonator and can get stuck after getting to the top and dropping down on the other side | hit the detonator during the small cubes sequence | Player cannot scale the rocks after hitting the detonator | Player can scale the rocks after hitting the detonator and can drop down on the other side getting stuck | High
walk against the rocks
get to the top
drop down on the other side
Locnew 77 | Dialogue with Danny on day 2 can be started without him being there | During the Special Investigation on day 2, if player goes to Travis Ultrasound and to Wes Cornfoot and misses Danny, Cliff will still appear to finish the Special Investigation. After the tractors are moved away to access the back of the ranch, player can still talk to Danny to ask questions | Start the Special Investigation on day 2 | Player needs to talk to everyone during the Special Investigation | Player does not need to talk to Danny during the Special Investigation but after it's concluded, Danny's dialogue can be triggered even though he's not there | Low
talk to Travis Ultrasound
talk to Wes Cornfoot
talk to Cliff under the Ranch board
complete the dialogues until the back of the ranch is accessible
talk to Danny at the tractor
Locnew 78 | Player can access the cave on day 5 before Cliff | If player triggers Cliff to go in the mines but does not wait until he gets there but triggers the dialogues about Danny, Cliff's dialogue about getting to the mine will mix into the dialogue about Danny and Metrixia's dialogue will not start | Trigger Cliff to start going into the mines | Player can only access the mines after Cliff | Player can access the mines before Cliff if Cliff starts going in but player triggers the dialogue about Danny | Medium
Go near Danny to start the dialogue of him loading the cargo
finish the dialogues
walk into the mine
Locnew 79 | Cliff's character artwork changes on day 5 | If Cliff gets inside the mines but player triggers the dialogue about Danny loading the cargo, Cliff's character artwork will be his regular instead of the one with the horse mask | Trigger Cliff to start going into the mines | Character artworks do not change during a day | Cliff's character artwork changes if he gets inside the mines but player triggers the dialogue about Danny | Low
Wait until Cliff gets inside the mines
Go near Danny to start the dialogue of him loading the cargo
Locnew 80 | Triggering dialogue about Danny on day 5 before Cliff decides to go into the mines causes player to get stuck | If player triggers the dialogue on day 5 about Danny loading the cargo before triggering Cliff to go into the mines causes the dialogue to not go further than one sentence | Shoot on camera all the townsfolk | Player does not get stuck if a dialogue is triggered early | Player gets stuck if the dialogue about Danny loading the cargo is triggered before Cliff decides to go into the mines | High
Go up to Danny on the main path
Locnew 81 | Sprinting into the police department on day 3 from the parking lot makes player get halved on doorstep | On day 3, going into the police department while holding LSHIFT from the department's parking lot makes player to get halved on the doorstep until player tries getting inside from different angles. This does not happen if player holds LSHIFT after already leaving the parking lot or if player does not hold the LSHIFT at all | get to the police department's parking lot on day 3 | Player is not halved on buildings that are meant to be get inside | Player is halved on the doorstep while sprinting inside to the police department from the parking lot | Low
Press and hold LSHIFT
walk inside the department
try walking inside from different angles still at the doorstep
Locnew 82 | Back of a truck on day 1 has no collision | The back of a truck on day 1 has no collision and player can walk into it until the wheels | walk up to the back of the truck | All objects have collision | The back of a truck on day 1 has no collision | Low
Walk into it