## Bugs
Bug Report
Project Details
Description |  |  | Voluntary Beta Testing
Testers, contacts |  |  | Benedek Sándor Seres, benedek.seres@gmail.com Lilla Seres, seres.lilla1@gmail.com
Testing Date |  |  | 19-Sept-23 - 24-Sept-23
Test Environment |  |  | Steam, Win 11, Prologue 2.0
UX Suggestions
BugID | Short Description | Description | Steps for Reproduction | Expected Result | Actual Result | Priority | SuggestionID | Description | Suggestion
BulletBug 1 | Spelling mistake in prologue | The Fate will always find it's way back to you should be Fate will always find it's way back to you its way back to you | Start the prologue | …its way… | …it's way… | Low | BulletUX 1 | The text height is too big and the text boxes are too small so a longer text will start shrinking while the player is reading it | Adding one or two rows to the textboxes may solve this
BulletBug 2 | The blur effect on the prologue level also affects the player character model | The blur effect that surrounds the house the prologue level plays on, also affects the player character model | start the prologue | Characters are not affected by the blue effect surrounding the house on the prologue level | The player character model is affected by the blue effect | Low | BulletUX 2 | Music turning down during weapon selection might take out player from the flow of music and shooting | If the music did not stop but was slowed down and given a different sound effect may not take out the player from the rhythm of the combat
walk around the edges of the house
|  |  | check the player character model receiving the blur effect at the hand or torso |  |  |  | BulletUX 3 | The main character making damage sound whenever getting damaged might bother some players in the long run | If the main character only made damage sounds after 3-4 hits, it may not be as bothering
BulletBug 3 | getting stuck in the offices | sliding to specific office tables on level Office Party causes player to get stuck | slide to the side of the office table that is on the corner in the office room with the red carpet | Player cannot get stuck between objects | player can get stuck in several office desks in the Office Party level | High
slide between the desk and chair in the office room with the green carpet
slide to the right side of the desk in the bottom-middle in the office room where the first enemy appears with the rocket launcher
slide to the left side of the desk in the bottom-right in the office room where the first enemy appears with the rocket launcher
BulletBug 4 | On Office Party, there is no combat music in the office room with the blue carpet | When player first enters the office room with the blue carpet on level Office Party and starts fighting the enemies, there is no combat music | enter the office room that has the blue carpet | there is combat music while fighting | on level Office Party in the office room with the blue carpet, there is no combat music | Low
BulletBug 5 | Player can slide into the back of the trucks on Office Party | On Office Party, player can slide into the back of the trucks. This seems to happen at random and I could not determine how much earlier player needs to start sliding to glitch into the object | get to a section where there are trucks where enemies spawn from | Player cannot glitch into objects | On level Office Party, player can slide into the back of the truck | Medium
wait until the truck stops
slide into its back
BulletBug 6 | Characters with moving animations do not stop on Pause | The player character and the mini-mech characters move in place when the Pause Menu is brought up | Encounter a Mini-mech | All characters stop when the game is paused | when the pause menu is brought up while the player character or a mini-mech character is moving, they remain in their moving animation | Low
Pause the game when both the player and a Mini-mech are running
BulletBug 7 | Breaking In - The hacking section can be bypassed | On Breaking In, the hacking section at the beginning of the Server Room can be bypassed by going against the wall the machine to hack is mounted on. While going against the wall move the cursor right a little. Upon getting to the checkpoint, the bridge extends. This works from the other end too. | start level Breaking In | the hacking section cannot be bypassed | The hacking section can be bypassed by walking up against the wall and moving the cursor a little right | Medium
go to the server room
stand in front of the machine that needs to be hacked
move the cursor a bit right
start walking against the wall
BulletBug 8 | Logistical Nightmare - Text missing from text bubble | When starting Logistical Nightmare, Jack says 'Oh boy… this place feels like […]' but in his text bubble he only says 'This place feels like […]' | Start level Logistical Nightmare | the text bubbles contain everything the characters say | on Logistical Nightmare, when Jack says 'Oh boy… this place feels like […]' in the beginning of the level, the 'Oh boy…' is missing from the text bubble | Low
go to the first door to trigger his speech
BulletBug 9 | Logistical Nightmare - Spelling mistake | There is a missing space between 'of course' after Jack explains his usual approach to problems | Start level Logistical Nightmare | …of course | … ofcourse | Low
go to the first railway line
check the last text bubble in the triggered dialogue
BulletBug 10 | Logistical Nightmare - missing combat music in turquoise carpet office room | There is no combat music on Logistical Nightmare in the office room that has the switch to turn off the lasers to reach the end of the level | Start level Logistical Nightmare | there is combat music while fighting | In the office room with the turquoise carpet, there is no combat music | Low
get to the office room with the turquoise carpet
BulletBug 11 | Turrets of Mechanics are not damaged by rolling a barrel to them | When player pulls a barrel to itself and redirects it to a turret that a Mechanic put down, the barrel goes through the turret | wait until a Mechanic puts down a turret | enemies are damaged by the rolling barrels | turrets of Mechanics are not damaged by rolling barrels | Medium
Pull a barrel to yourself
redirect it to the turret
BulletBug 12 | Player can get on the beginning of railways but will not move and the end of railways stuck the player | If player gets on the beginning of a railway, the character will do so but will not move. Also, if player is riding the railway and gets to the end of it, player is stuck for some moment on the end of the railway | get on the railway on the beginning of it | player does not get stuck on the beginning or the end of it | Player gets stuck for some moment if it tries to get on the beginning of the railway or the end of it | Medium
get on the railway and do not jump off it
BulletBug 13 | The Mini-mech enemy can freeze if player pulls them into a pit | By pulling the Mini-mech enemy to a pit, it is stuck there for some time but launches itself out. However, after that, it is frozen in place. It can be killed but the character will remain there and the game does not proceed even though its HP has hit zero. Player needs to truly kill it either with the melee finishing attack or by pulling it into a pit again | pull a Mini-mech to yourself | enemies either die or jump out of pits if player pull them in | The Mini-mech gets stuck in the pit for some time, launches itself out and the character does not explode after the explosion effect | Medium
run to the nearest corner of the pit and let go of the Mini-mech while it's above the pit
wait until it launches itself out of the pit
shoot it until the explosion animation is triggered
kill it with the finishing melee attack or repeat step one and two