## Sheet1
Defect Report
Project Details
Description |  |  | Voluntary Beta Testing
Tester, contact |  |  | Benedek Sándor Seres, benedek.seres@gmai.com
Testing Date |  |  | 15-07-2023 - 16-07-2023
Test Environment |  |  | Beta version
BugID | Short Description | Description | Steps for Reproduction | Expected Result | Actual Result | Priroty
Locnew 1 | Clipping through tire swing model hanging from tree | the tire swing that is hanging from the tree behind the house the game's first quest takes place is not solid and player can clip through it | Go behind the house the first quest takes place | the tire swing model is solid | the tire swing model is not solid and player can go through it | Low
find the tire swing
go through it
Locnew 2 | Missing collision | There is a minor collision missing between the mountain and the grass at the end of the street where the white school bus is | get to the back of the house behind the white school bus | all terrain has collision | back of the house near the white school bus has missing collision | Medium
go to the trees near where the mountain starts
Locnew 3 | Pause menu overlapped by the Day title | Starting a day and pausing the game during the Day title causes the pause menu to be overlapped | Start a day | the pause menu overlaps everything | the pause menu is overlapped by the day title | Medium
pause the game when the Day title appears
Locnew 4 | Triggered sounds do not stop when game is paused | Triggered sounds do not stop while the game is paused, causing the objects complete their scripted event without sound in the end | find an object with a scripted event and sound | Triggered sounds are paused while the game is paused | Triggered Sounds keep playing while the game is paused | Medium
pause the game
continue playing
wait for the object to finish its routine
Locnew 5 | Mouse is too sensitive | The default sensitivity of the mouse is set too high, making it difficult to do slight look-arounds | Move the mouse vertically with default sensitivity | Default mouse sensitivity allows player to do slight look-arounds | Looking around nicely with default mouse sensitivity is difficult | Medium
Move the mouse horizontally with default sensitivity
Locnew 6 | Music volume of main menu is lower when player enters main menu from the game | Music volume main menu is higher when player starts the game than when player actually plays the game and goes back to the main menu | start the game | Main menu music always has the same volume level | Main menu music is quieter when player enters the main menu from playing | Low
start playing
go back to the main menu
Locnew 7 | Player can go up steep terrain | Player can go up very steep terrain which is unrealistic to the game world's physics. This also allows the player to get near the edge of the world | find a mountain | Player cannot go up very steep terrain | Player can go up very steep terrain and gets to see the edge of the world | Medium
go up the mountain
Locnew 8 | Mouse Y sensitivity is not equally sensitive as Mouse X's on controller | Horizontally the camera is more sensitive than vertically even if they are set to the same level on a controller | set the Mouse Y sensitivity and Mouse X sensitivity to the same level | Horizontal and vertical sensitivity on the same level are equally sensitive | Horizontally the camera sensitivity is more sensitive than vertically even if they are set to the same level | Medium
start playing with a controller
look slightly vertically
look slightly horizontally
Locnew 9 | The explosion on the subscriber number is delayed | When first meeting Cliff Rockslide he mentions the subscribers and how many he aims to have but the effect of explosion happens after he starts changing the subject | meet Cliff Rockslide on Day 1 | The explosion on the number of subscribers happen when he mentions this feature | The explosion on the number of subscribers happen after he talks about money as motivation | Low
talk to him until he mentions the subscribers
see the explosion when he talks about economical gain as motivator
Locnew 10 | Pressing ESC during dialogue option causes player to get stuck | Pressing the ESC button when player gets to say Yes or No during conversation causes the dialogue to stop and player is stuck | get into a conversation | Pressing ESC during dialogue options does not do anything | Pressing ESC during dialogue options causes the dialogue to stop | High
Press ESC when Yes or No options are presented
Locnew 11 | NPC in café does not move | the NPC that is sitting inside the café with a coffee and a book does not move | get to the café | NPCs have natural moving | NPC in café is sitting steady | Low
find the NPC inside the café with a book and coffee
Locnew 12 | Player is pushed up when standing in the way of Cliff Rockslide | When Cliff starts running and player is in the way, Cliff will push the player up | Get ahead of Cliff when he starts running | Cliff Rockslide does not collide with the player | Cliff Rockslide collides with the player causing a glitch | High
Let Cliff get ahead of player
Locnew 13 | Number of subscribers do not reset | The number of subscribers do not reset after gaining at least one on day one and quitting then continuing the game | Retrieve the camera on day 1 | The number of subscribers resets to the number player had before player quitted | The number of subscribers does resets to the number player had before player quitted | Medium
Gain at least one additional subscriber
quit to the main menu
Continue playing by using the Continue function
Retrieve the camera on day 1
check the number of subscribers
Locnew 14 | Lady runs into the mountain after explosion at gas station | After the explosion on day 1, there is a lady that runs aways into the forest and then clipping into the mountain | get to the explosion on day 1 | NPCs do not clip into textures | Lady at the explosion at the gas station runs and clips into the mountain texture | Low
go to the explosion site but do not start the interactions
check a lady running away and follow it
Locnew 15 | The car of the exploded barrel only appears at the moment of explosion | On day 1, the car that has the exploded barrel appears after the explosion and is not in the world prior to it | Finish the dialogue with the officers after reporting the pumpkin | the car that has the barrel that explodes is somewhere around the location it appears in | the car that has the barrel that explodes is nowhere in the world | Low
Locnew 16 | the given stars after reporting can be zoomed at | after completing a report, the player can zoom at the given stars | complete a reporting | the given stars after reporting have a fixed position | the given stars after reporting can be zoomed at | Medium
focus on the given stars
Locnew 17 | Quitting after the car ride is over after wolf chase and continuing causes game to present allow player to play two missions at once | After Cliff is chased by the wolf, gets in the car and gets out at his garage, player can quit. If player hits Continue in the main menu and completes the pumpkin reporting, Cliff will be there to go to the house where the wolf is and he is also there with the officers at the café | Complete the wolf chase sequence and play until Cliff is dropped of at his garage | Quitting and continuing the game resets the completed reports to the beginning of the day | Quitting and continuing the game after wolf chase sequence causes game to offer player to play two missions at the same time | High
quit to the main menu
Continue the game from the main menu
Complete the pumpkin reporting
go to the gas station where Cliff is waiting to go to the house with the wolf in it
go to the café where Cliff is there with the officers
Locnew 18 | Character artwork does not change from Clarence on day 1 | When Cliff and Clarence gets into their dialogue on day 1, the character artwork does not change when Cliff talks | meet Clarence on Day 1 | The character artwork changes based on who is talking | During the dialogue between Cliff and Clarence, only the artwork of Clarence is on screen | Medium
start the conversation between Cliff and Clarence
Locnew 19 | Player can move freely while talking to Oaklyin on day 1 | While talking to Oaklyin on day 1, player can move during the conversation | Start talking with Oaklyin after the explosion on Day 1 | Player cannot move around while in dialogue | Player can move around while in dialogue with Oakliyn | Low
move away
Locnew 20 | The Music volume in the settings changes inconsistently | Turning the Text volume or the SFX volume all the way up, causes the Music volume to go very quiet. This also works if the Music volume is turned down by 1 | Change the music volume by one or change the text volume/SFX volume to max | Changing a volume setting in the options only changes the chosen volume and only one bit at a time | Changing the SFX-Text volume to the max changes the music volume very quiet. This also happens if the Music volume is turned down by 1 | Medium
Locnew 21 | The default SFX volume is the loudest option on the slider | Changing the SFX volume from the default volume causes the volume to go quiet. Even on max volume, the default volume is the loudest | Start the game with the default SFX volume (or change it back to the default and relog to the game) | Changing the default SFX volume causes the SFX volume to go either louder or quieter | Changing the default SFX volume causes the SFX volume to go quieter | Medium
listen to the SFX volume
go back to the main menu
change the SFX volume
start the game
listen to the SFX volume
Locnew 22 | Watching through the opening credits causes the game to start with quieter Music volume | Watching through the opening credits makes the game start with quieter Music volume than when player clicks through it | Launch the game | The music volume does not change unless player changes it | The music volume goes quieter if player watches through the opening credits | Medium
watch through the opening credits
listen to the Music volume
quit from the game to the desktop
launch the game again
skip through the opening credits as soon as the game allows
listen to the Music volume
Locnew 23 | Small dog on day 1 cannot be interacted with | The small dog near the giant pumpkin cannot be interacted with as it cannot be captured for Barking News. It also looks like it's barking it has no sound | Find the small dog on Day 1 | Small dog on day 1 can be interacted with and makes barking sound | Small dog on day 1 has no sound and cannot be interacted with | Low
Locnew 24 | Firefighter is not sitting on box | The firefighter near where the explosion will take place at the gas station of day 1 is not sitting on the box | Find the firefighter near the gas station | NPCs match the height of objects they are sitting on | The firefighter on day 1 is not sitting on the box | Low
Locnew 25 | Police car at the end of day 1 can be clipped through | After the officer takes Cliff home at the end of day 1, her can clipped through | Finish the wolf chase sequence | Objects are solid | Police car at the end of day 1 can be clipped into | Low
after Cliff is taken home, follow the police car
Locnew 26 | Abby clips into her chair on day 2 | When meeting Abby the first time in the game, when she talks, she clips into her chair | Meet Abby on day 2 | NPCs do not clip into textures | Abby clips into her chair on day 2 | Low
Get into a dialogue with her
Locnew 27 | Player is pushed up walking into the giant pumpkins on day 2 | On day 2, walking into the giant pumpkins near the campfire with the four NPCs causes player to be pushed up | Finish the dialogue with Lyla after their father finishes repairing the car | Walking into objects stops player | Walking into the giant pumpkins on day 2 at the back of the farm causes player to be pushed up | Medium
go to the back of the farm
find the giant pumpkins near the campfire
Locnew 28 | SFX volume decreases Text volume | the text volume is normal but goes quieter as soon as an SFX volume is triggered | Get into a dialogue | Text volume is constant | Text volume goes quieter after SFX volume trigger | Low
Listen to the volume of texts
Trigger an SFX volume
Listen to the volume of texts
Locnew 29 | Chilly spawned outside the fences | Chilly the penguin can spawn out of bounds on day 2 | Talk to the Shady Character and successfully start the sequence to look for his penguin | Objects necessary for day completion are inside the player's reach | Chilly once spawned outside the fences where the player cannot get to | Medium
Check if the penguin spawned out of bounds
Locnew 31 | Accessing the giant onion early on day 2 | On day 2 the tractor that is blocking the back of the map can be walked around. This also allows the player to skip the early dialogues | Walk up the fence at the tractor | Objects blocking roads cannot be bypassed | On day 2 the tractor blocking the back of the map can be bypassed | Medium
go along the fence for as long as possible
turn around and go along the fence on the other side for a few meters
Locnew 32 | Getting out of bounds and fall out of the world on day 2 | On day 2, after getting to the back of the farm, player can walk up the mountain. This allows the player to get out of bounds and eventually fall out of the world | get to the back of the farm | Player is blocked from getting out of bounds | Player can get out of bounds on day 2 | Medium
walk forward up to the mountain and at the edge of the world
Locnew 33 | Player can push Lyla and Cliff | Walking into Cliff causes him to run back facing the player while Lyla glithces away if player does the same | Finish the dialouge with Rose and Lyla | NPCs do not get pushed away if player walks against them | Lyla and Cliff get pushed away if player walks against them | Low
Walk against Cliff
Walk againt Lyla